## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
Gated Community ERM(Enterprise Resource Management) |  | 30 | 2021-08-27 | 2021-09-27 | 2021-09-29
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design
1.1 | Project Defination | 2021-08-27 | 2021-08-28 | 2
1.2 | Finish webpage | 2021-08-29 | 2021-08-30 | 2
1.3 | Project Design | 2021-08-31 | 2021-09-02 | 3
2 | Coding
2.1 | Phase 1 | 2021-09-03 | 2021-09-12 | 10
2.2 | Phase 2 | 2021-09-11 | 2021-09-19 | 9
2.3 | Additional Features | 2021-09-20 | 2021-09-21 | 2
3 | Testing
3.1 | Phase 1 Testing | 2021-09-22 | 2021-09-22 | 1
3.2 | Modification /Any changes | 2021-09-23 | 2021-09-23 | 1
3.3 | Phase 2 Testing | 2021-09-24 | 2021-09-24 | 1
3.4 | Modification /Any changes | 2021-09-25 | 2021-09-25 | 1
3.5 | Final Testing | 2021-09-26 | 2021-09-26 | 1
4 | Documentation
4.1 | User Guide | 2021-09-26 | 2021-09-26 | 1
4.2 | Presentation | 2021-09-27 | 2021-09-27 | 1

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Team Lead
| Member Name | Aditya Vilas Abu
| PRN No | 210543181002
| Description | Services(CRUD operations) and UI using React,Css,Bootsrap,Html
2 | Role | Team Member
| Member Name | Vaishnavi Pramod Thorat
| PRN No | 210543181116
| Description | Database Using Hibernate and UI using React,Css,Bootsrap,Html
3 | Role | Team Member
| Member Name | Rina Kisan Borchate
| PRN No | 210543181078
| Description | Database Using Hibernate and UI using React,Css,Bootsrap,Html
4 | Role | Team Member
| Member Name | Shraddha Vilas Sabne
| PRN No | 210543181104
| Description | Controllers and UI using React,Css,Bootsrap,Html